## Sheet1
Task | Start Date | Duration
Complete Abstract | 2012-09-10 | 4
Complete One Slide | 2012-09-18 | 2
Investigation of Software/Hardware Costs | 2012-09-19 | 7
Investigation of Personnel/Real Estate Costs | 2012-09-19 | 7
Investigation of Funding Methods | 2012-09-19 | 7
Final Design of Logo and Trademark Material | 2012-09-21 | 7
Initial Investigation of Costs | 2012-09-21 | 10
Mock-Ups of Games | 2012-09-21 | 14
Risk Assessment of Project | 2012-09-30 | 14
Project Analysis and Impact | 2012-10-15 | 14
Preparation of Figures for Final Report | 2012-10-20 | 10
Prepare Final Draft | 2012-10-25 | 9
Final Revisions for Submission | 2012-11-02 | 7